HUB32

SCHOOL MANAGEMENT PLATFORM

Tài liệu Triển khai & Phát triển Dự án Chi tiết

Phiên bản: 2.0  |  Ngày: 26/03/2026

INTERNAL – Project Development Team Only

Kiến trúc: WebRTC SFU (mediasoup) + C++ Agent + REST API

Mục tiêu: Quản lý toàn trường, 200+ PC, zero VNC, zero Qt

# MỤC LỤC

# 1. TỔNG QUAN DỰ ÁN

## 1.1. Giới thiệu

HUB32 là nền tảng quản lý phòng máy trường học, cho phép giáo viên giám sát và điều khiển tất cả máy tính học sinh trong một hoặc nhiều phòng máy qua giao diện web. Hệ thống sử dụng kiến trúc SFU (Selective Forwarding Unit) với mediasoup để truyền màn hình thời gian thực, không cần transcode, giảm tải CPU máy chủ đáng kể.

## 1.2. Mục tiêu chiến lược

- Quản lý toàn trường: nhiều phòng máy, nhiều tòa nhà, 200+ PC đồng thời

- Streaming màn hình thời gian thực: độ trễ < 500ms, H.264 SFU không transcode

- Điều khiển từ xa: khóa màn hình, gửi tin nhắn, tắt/khởi động lại, mở ứng dụng/web

- Zero install cho giáo viên: chỉ cần trình duyệt web (Chrome/Edge/Firefox)

- Bảo mật: JWT RS256, TLS, argon2id, audit log đầy đủ

- Hiệu suất: binary C++ nhỏ gọn (~12MB server, ~12MB agent), không Qt/VNC

## 1.3. Các thành phần chính

| Thành phần | Ngôn ngữ | Mô tả | Trạng thái |
| --- | --- | --- | --- |
| hub32api-server | C++17 | REST API + mediasoup SFU + SQLite | ~35% |
| hub32-agent | C++17 | Win Service: DXGI capture, features, WebRTC | ~95% |
| Teacher Dashboard | JavaScript | Web: mediasoup-client.js, grid view, control | 0% |
| coturn | C | STUN/TURN relay cho NAT traversal | Chưa deploy |

# 2. KIẮN TRÚC HỆ THỐNG CHI TIẾT

## 2.1. Tổng quan kiến trúc

Hệ thống gồm 3 tầng: VPS (server + SFU + TURN), Student PCs (agent), Teacher Browser (web dashboard). Giao tiếp qua HTTPS (REST API) và WebRTC (media stream). mediasoup làm SFU, chỉ forward H.264 packets mà không transcode, giảm CPU server đáng kể.

## 2.2. REST API Layer

Sử dụng cpp-httplib (BSD, header-only) với SSLServer cho TLS. Tất cả endpoints yêu cầu JWT Bearer token, ngoại trừ /api/v1/auth/login.

| Endpoint Group | Mô tả | Auth Level |
| --- | --- | --- |
| /api/v1/auth | Login, refresh, logout, revoke | Public/User |
| /api/v1/schools | CRUD trường học | Admin |
| /api/v1/locations | CRUD phòng máy/lab | Admin |
| /api/v1/computers | Trạng thái máy tính | Teacher |
| /api/v1/teachers | Quản lý giáo viên | Admin |
| /api/v1/agents/* | Agent registration, heartbeat, commands | Agent |
| /api/v1/stream/* | WebRTC signaling | User |
| /api/v1/features | Điều khiển lock/msg/power | Teacher |
| /api/v2/batch/* | Batch operations | Admin |
| /api/v2/metrics | Prometheus metrics | Admin |
| /api/v2/audit | Audit log | Admin |

## 2.3. mediasoup C++ SFU Integration

mediasoup là SFU WebRTC hiệu suất cao, worker viết bằng C++ trên libuv. Từ v3.13.0, dùng FlatBuffers thay JSON để giao tiếp giữa app layer và worker – giảm CPU, tăng type safety.

Phương án tích hợp (khuyến nghị): Embed worker vào process

- Clone mediasoup worker source làm submodule, build static library với Meson

- Gọi mediasoup_worker_run() trong thread riêng, giao tiếp qua ChannelReadFn/ChannelWriteFn

- FlatBuffers serialize/deserialize cho mọi lệnh

- Tham khảo: github.com/ouxianghui/mediasoup-server – C++ SFU đầy đủ với FlatBuffers + pipe/callback

Cấu trúc Router/Room:

- 1 Worker = 1 CPU core; 1 Router = 1 Room/Location

- Mỗi student = 1 WebRtcTransport (producer) với H.264 simulcast 3 layers

- Mỗi teacher = 1 WebRtcTransport (consumer) cho mỗi room đang xem

- Router được tạo on-demand, hủy khi room trống

WebRTC Signaling Flow – Agent (Producer):

- POST /api/v1/stream/transport → tạo WebRtcTransport, trả ICE + DTLS params

- POST /api/v1/stream/transport/:id/connect → DTLS handshake

- POST /api/v1/stream/produce với RTP params → tạo Producer, trả producerId

- Agent gửi H.264 RTP packets qua WebRTC transport

WebRTC Signaling Flow – Teacher (Consumer):

- POST /api/v1/stream/transport → tạo consumer transport

- POST /api/v1/stream/transport/:id/connect

- POST /api/v1/stream/consume với producerId + RTP capabilities → tạo Consumer

- Teacher nhận H.264 stream, hiển thị trong <video> element

## 2.4. hub32-agent (Windows)

Pipeline: DXGI Capture → NV12 Convert → H.264 Encode → WebRTC Stream

- AcquireNextFrame() → ID3D11Texture2D từ GPU (BGRA format)

- D3D11 Compute Shader hoặc libyuv: BGRA → NV12

- H.264 encode: NVENC (NVIDIA) → QSV (Intel) → x264 ultrafast (CPU fallback)

- Simulcast 3 layers: 150kbps (thumbnail), 500kbps (medium), 2500kbps (full)

- RTP packetize và gửi qua libdatachannel WebRTC transport

libdatachannel: thư viện WebRTC nhẹ (C++17, ~500KB), tương thích Firefox/Chromium/Safari. License MPL 2.0. Chỉ cần OpenSSL/GnuTLS. ICE qua libjuice (submodule). Hỗ trợ SRTP, DTLS, SCTP multiplexing theo RFC8843.

Feature Handlers:

| Feature | WinAPI | Mô tả |
| --- | --- | --- |
| ScreenLock | Fullscreen Overlay + HWND_TOPMOST | Khóa màn hình |
| InputLock | BlockInput(TRUE) | Khóa chuột + bàn phím |
| MessageDisplay | MessageBoxW() | Hiển popup |
| PowerControl | ExitWindowsEx() | Shutdown/Reboot/Logoff |
| AppLauncher | ShellExecuteW() | Mở ứng dụng |
| WebOpener | ShellExecuteW() | Mở URL |

## 2.5. coturn TURN Server

coturn là TURN/STUN mã nguồn mở phổ biến nhất, tuân thủ RFC 5389/5766. Trong môi trường trường học với firewall chặt, TURN qua TLS port 443 là bắt buộc.

Cấu hình khuyến nghị:

- listening-port=3478 (STUN), tls-listening-port=443 (TURN TLS)

- use-auth-secret với HMAC time-limited credentials (TURN REST API)

- min-port=40000, max-port=49999 (relay UDP range)

- Let’s Encrypt certificate, auto-renewal với certbot

- denied-peer-ip=10.0.0.0-10.255.255.255 – ngăn relay vào internal network

- no-tcp-relay – không cần cho WebRTC

- setcap cap_net_bind_service=+ep /usr/bin/turnserver – bind port 443 không cần root

Bảo mật (coturn 4.7.0+, khuyến nghị Enable Security 02/2026):

- Mặc định tắt TLS 1.0/1.1, ẩn software attribute – secure-by-default

- no-rfc5780 mặc định – giảm unauthenticated response surface

- Realm ngắn (ví dụ: realm=t) – giảm amplification

- Cập nhật thường xuyên: CVE-2025-69217, CVE-2020-26262

# 3. MÔ HÌNH DỮ LIỆU

## 3.1. Tổng quan

3 file SQLite riêng biệt, WAL mode bắt buộc:

| Database | Mục đích | Backup |
| --- | --- | --- |
| school.db | Schools, locations, computers, teachers, sessions | Daily → S3 |
| audit.db | Audit log (mọi hành động) | Daily |
| tokens.db | JWT revocation list | Không cần (tự cleanup) |

## 3.2. Schema

school.db:

schools(id PK, name, address, created_at)

locations(id PK, school_id FK, name, building, floor, capacity, type)

computers(id PK, location_id FK, hostname, mac_address, ip_last_seen,

agent_version, last_heartbeat, state, position_x, position_y)

teachers(id PK, username UNIQUE, password_hash[argon2id], full_name, role, created_at)

teacher_locations(teacher_id FK, location_id FK) -- composite PK

active_sessions(computer_id PK/FK, user_login, user_fullname, session_start,

producer_id, transport_id)

audit.db:

audit_log(id AUTO, timestamp, teacher_id, action, target_type, target_id, details JSON, ip_address)

tokens.db:

revoked_tokens(jti PK, revoked_at, expires_at) -- auto-cleanup khi hết hạn

## 3.3. Cải tiến schema

- Thêm computer_groups: nhóm máy tính trong 1 phòng (nhóm A, nhóm B)

- Thêm scheduled_tasks: hẹn giờ tự động (tắt máy cuối giờ, khóa khi thi)

- Index: idx_computers_location, idx_audit_timestamp, idx_heartbeat

# 4. TRẠNG THÁI HIỆN TẠI

## 4.1. hub32api-server (~35%)

| Component | Status | % Code | Ghi chú |
| --- | --- | --- | --- |
| REST API framework | DONE | 95% | cpp-httplib OK |
| JWT Auth | DONE but buggy | 80% | Xóa HS256 fallback |
| Controllers v1 | DONE (mock) | 70% | Cần kết nối SQLite |
| Controllers v2 | DONE (mock) | 60% |  |
| Middleware | DONE (race) | 85% | Fix std::atomic |
| Config system | DONE | 90% |  |
| Hub32CoreWrapper | STUB | 0% | Thay bằng SQLite |
| AuditLog | PARTIAL | 60% | Fix error handling |
| mediasoup | NOT STARTED | 0% | Phase 3 |
| School model | NOT STARTED | 0% | Phase 1 |
| WebRTC signaling | NOT STARTED | 0% | Phase 3 |

## 4.2. hub32-agent (~95%)

| Component | Status | Lines | % Code |
| --- | --- | --- | --- |
| DXGI Screen Capture | DONE | 703 | 100% |
| GDI Fallback | DONE | incl. | 100% |
| ScreenLock | DONE | 338 | 100% |
| InputLock | DONE | 121 | 100% |
| MessageDisplay | DONE | 234 | 100% |
| PowerControl | DONE | 184 | 100% |
| CommandDispatcher | DONE | 113 | 100% |
| AgentClient REST | DONE | 437 | 100% |
| WinServiceAdapter | DONE | 292 | 100% |
| Config | DONE | 185 | 100% |
| FFmpeg H.264 | NOT STARTED | 0 | 0% |
| libdatachannel | NOT STARTED | 0 | 0% |

## 4.3. Teacher Dashboard (0%)

Chưa bắt đầu. Cần: mediasoup-client.js, grid view, feature control panel, admin panel.

# 5. KẾHOẠCH TRIỂN KHAI

## 5.1. PHASE 0: Security Fix (Tuần 1)

CRITICAL – Bắt buộc trước khi deploy internet

- [SECURITY] Xóa HS256 fallback – RS256 only với RSA 4096-bit

- [SECURITY] OpenSSL RAND_bytes thay mt19937

- [SECURITY] Xóa hardcoded admin role (AuthController.cpp:102)

- [SECURITY] argon2id password hashing

- [SECURITY] TLS (cpp-httplib SSLServer)

- [BUG] Fix race condition rate limiter (std::atomic::fetch_add)

- [BUG] Fix TokenStore: steady_clock vs system_clock

- [BUG] Fix AuditLog SQLite error handling

- [HARDENING] Input validation, config fail-on-error, persistent revocation

## 5.2. PHASE 1: Database + School Model (Tuần 2)

- SQLite schema: school.db, audit.db, tokens.db (WAL mode)

- Repository pattern: SchoolRepo, LocationRepo, ComputerRepo, TeacherRepo

- Thay Hub32CoreWrapper mock bằng SQLite

- CRUD API cho schools, locations, teachers, computers

- Role-based access: admin=all, teacher=assigned rooms

## 5.3. PHASE 2: Agent Communication (Tuần 3)

- Registration: MAC + hostname → computer ID

- Heartbeat: 30s interval, 3x timeout = offline

- Command queue: enqueue → poll → execute → result

- Integration test: register → online → lock → success

## 5.4. PHASE 3: mediasoup SFU (Tuần 4–5)

- Build mediasoup worker static library (Meson)

- MediasoupManager: worker thread, FlatBuffers communication

- RoomManager: 1 Router/location, on-demand create/destroy

- Signaling API: transport, connect, produce, consume, cleanup

- coturn: STUN 3478, TURN TLS 443, relay 40000-49999, HMAC credentials

## 5.5. PHASE 4: Agent WebRTC Producer (Tuần 5–6)

- FFmpeg libavcodec: NVENC → QSV → x264 fallback

- BGRA → NV12 (D3D11 compute shader / libyuv)

- libdatachannel: WebRTC producer với H.264 RTP, simulcast 3 layers

- Auto-reconnect, bandwidth adaptation

## 5.6. PHASE 5: Teacher Dashboard (Tuần 6–7)

- Vanilla JS + mediasoup-client.js, served bởi nginx

- Login → JWT → Room selector → Grid view (<video> per student)

- Thumbnail (low layer) / Fullscreen (high layer)

- Control panel: lock, message, power, open web/app

- Admin panel: manage schools, locations, teachers, audit

## 5.7. PHASE 6: Demo Mode (Tuần 7–8)

- Teacher getDisplayMedia() → mediasoup produce → SFU → all students

- Agent nhận stream qua libdatachannel, fullscreen overlay

## 5.8. PHASE 7: Testing (Tuần 8–9)

- Unit tests, dependency injection refactor

- Load test: 200 agents, 5 teachers

- Security audit: JWT, TLS, SQL injection

- Monitoring: Prometheus + Grafana

## 5.9. PHASE 8: Deployment (Tuần 9–10)

- Docker Compose: hub32api + coturn + nginx

- TLS Let’s Encrypt, agent MSI installer, auto-update

- Backup: SQLite WAL + daily

- Pilot: 1 room → full school

# 6. CẢI TIẮN ĐỀ XUẤT

## 6.1. WebRtcServer (mediasoup ≥ 3.11)

Nhiều WebRtcTransport chia sẻ 1 UDP/TCP port. Thay vì 400+ port cho 200 student, chỉ cần 1 port. Đơn giản firewall, giảm file descriptors, dễ Docker/K8s.

## 6.2. Adaptive Bitrate + transport-cc

mediasoup hỗ trợ transport-cc feedback. Agent implement sender-side bandwidth estimation, tự động giảm/tăng simulcast layer theo điều kiện mạng.

## 6.3. ICE consent checks (mediasoup 3.13.22+)

Phát hiện WebRTC disconnection silent (mất điện, rút dây) trong 5-30s thay vì đợi heartbeat timeout 90s.

## 6.4. Zero-Copy GPU Pipeline

DXGI → GPU Compute Shader (BGRA→NV12) → NVENC. Frame không rời GPU, CPU gần 0%.

## 6.5. Scheduled Tasks & Automation

- Tự động khóa màn hình khi thi, tắt máy cuối ngày, mở app theo lịch

- API: POST /api/v1/schedules với cron expression

## 6.6. Multi-VPS với PipeTransport

PipeTransport kết nối Router giữa các VPS. Mỗi VPS = 1 trường. Admin trung tâm xem tất cả.

## 6.7. Student Activity Monitoring

- Agent report active window title, foreground app

- Teacher thấy được student đang làm gì ngoài streaming

- Alert khi student mở app không được phép

## 6.8. File Distribution

- Teacher upload file → server → push tới tất cả agent trong room

- Dùng DataChannel của WebRTC cho file transfer nhỏ

- HTTP download cho file lớn

# 7. YÊU CẦU VPS & BANDWIDTH

| Tài nguyên | Tối thiểu (100 PC) | Khuyến nghị (200 PC) |
| --- | --- | --- |
| CPU | 4 cores | 8 cores |
| RAM | 8 GB | 16 GB |
| Bandwidth | 500 Mbps | 1 Gbps |
| Storage | 20 GB SSD | 50 GB SSD |
| OS | Ubuntu 22.04 | Ubuntu 24.04 |

Bandwidth worst case (1 teacher xem 200 PC):

| Hướng | Tính toán | Kết quả |
| --- | --- | --- |
| Ingress | 200 x 3.15 Mbps (3 simulcast layers) | 630 Mbps |
| Egress (5 teachers thumbnails) | 5 x 200 x 150 kbps | 150 Mbps |
| Egress (1 fullscreen) | 1 x 2,500 kbps | 2.5 Mbps |
| Tổng peak |  | ~800 Mbps |

Thực tế: teacher chỉ subscribe low layer (thumbnail) cho grid, high layer khi zoom. Bandwidth thực thường 200-400 Mbps.

# 8. TÀI LIỆU THAM KHẢO & TECH STACK

## 8.1. Tech Stack

| Layer | Technology | License | Size |
| --- | --- | --- | --- |
| REST API | cpp-httplib | BSD | ~100KB |
| JSON | nlohmann/json | MIT | ~50KB |
| Logging | spdlog | MIT | ~200KB |
| Auth | jwt-cpp + OpenSSL | MIT/Apache | ~3MB |
| Database | SQLite3 | Public Domain | ~1MB |
| SFU | mediasoup C++ worker | ISC | ~2MB |
| TURN | coturn | BSD | ~5MB |
| Capture | DXGI (Windows API) | N/A | 0 |
| Encode | FFmpeg NVENC/QSV/x264 | LGPL | ~5MB |
| WebRTC Client | libdatachannel | MPL-2.0 | ~500KB |
| Dashboard | vanilla JS + mediasoup-client | ISC | ~200KB |
| TLS Proxy | nginx | BSD | ~2MB |

## 8.2. Tài liệu tham khảo

mediasoup:

mediasoup Official Documentation v3

mediasoup GitHub (C++ SFU worker)

mediasoup-server C++ full implementation (ouxianghui)

libmediasoupclient C++ client library

mediasoup 3.13.0 FlatBuffers announcement

mediasoup Demo App

libdatachannel:

libdatachannel Official Site & Documentation

libdatachannel GitHub Repository

DXGI Desktop Duplication:

Microsoft Desktop Duplication API

DXGI Desktop Duplication Sample (Microsoft)

Desktop Recording with Hardware H.264 (MediaFoundation)

coturn:

coturn GitHub Repository

coturn Wiki - turnserver configuration

Securing coturn: Configuration Guide (Enable Security)

Self-Hosted STUN/TURN Best Practices (WebRTC.ventures)

WebRTC Standards:

RFC 7667 - RTP Topologies (SFU architecture)

RFC 8843 - SDP BUNDLE (multiplexing)

RFC 5766 - TURN Protocol

RFC 5389 - STUN Protocol

# 9. QUY TẮC LÀM VIỆC VỚI CLAUDE CODE

## 9.1. CLAUDE.md cho HUB32

CLAUDE.md là file đặc biệt Claude Code đọc đầu mỗi session. Đây là điểm leverage cao nhất để tăng chất lượng code.

Nội dung CLAUDE.md khuyến nghị:

# HUB32 - School Management Platform

## Tech: C++17, cpp-httplib, mediasoup, SQLite3, libdatachannel

## Build: mkdir build && cd build && meson setup .. && ninja

## Test: cd build && meson test

## Rules:

- std::string_view for params, not const std::string&

- ALL SQLite ops MUST check return codes

- spdlog for ALL logging, never std::cout

- JWT: RS256 ONLY, never HS256

- Validate input FIRST in every handler

- std::unique_ptr, no raw new/delete

- std::shared_mutex for read-heavy data

- For arch details: see docs/architecture.md

## Compact: preserve file list and test status

Nguyên tắc CLAUDE.md:

- < 150 dòng – quá dài = Claude bỏ qua

- Chỉ ghi những gì Claude hay làm sai

- Progressive Disclosure: chi tiết trong docs/*.md, CLAUDE.md chỉ chỉ đường

- Không dùng CLAUDE.md làm linter – dùng clang-tidy, clang-format

## 9.2. Quy trình bắt buộc

1. Plan trước, code sau:

Mọi task > 3 files: dùng Plan Mode trước. Review plan xong mới generate code.

claude> /plan Implement SchoolRepository với SQLite CRUD

2. Mỗi Phase = Session mới:

Tránh context pollution. Dùng /clear khi chuyển task.

3. Test ngay, test thường xuyên:

Sau mỗi thay đổi: meson test. Không commit nếu test fail.

4. Review từ fresh context:

Session mới để review – không bias từ quá trình viết code.

claude> Review SchoolRepository. Check: SQL injection, error handling, thread safety.

5. Quản lý context:

- /compact khi > 50%, kèm hướng dẫn giữ info quan trọng

- /clear khi chuyển task hoàn toàn

- Không để Claude đọc hàng trăm file không scope

## 9.3. Custom Commands

Tạo tại .claude/commands/:

security-check.md: Review security: JWT bypass, SQL injection, hardcoded creds

implement-repo.md: Implement SQLite repo cho $ARGUMENTS, theo pattern SchoolRepo

webrtc-debug.md: Debug WebRTC: ICE, DTLS, TURN, codec negotiation

## 9.4. Hooks

- PreToolUse: chặn commit nếu chưa chạy tests

- PostToolUse: tự động clang-format sau file edit

- Stop: kiểm tra output trước khi kết thúc turn

## 9.5. Prompting patterns

Interview-driven spec:

claude> I want to implement mediasoup signaling. Interview me.

Write spec to docs/spec.md. Then new session to implement.

Challenge-based review:

claude> Grill me on these changes. Check concurrent access, error

recovery, resource cleanup, security. Don't approve until satisfied.

Parallel sessions:

- Session A: implement feature

- Session B: viết tests độc lập

- Session C: review từ fresh context

# 10. SECURITY CHECKLIST

| Hạng mục | Yêu cầu | Status |
| --- | --- | --- |
| JWT Algorithm | RS256 only, RSA 4096-bit | NOT STARTED |
| JWT Secret | OpenSSL RAND_bytes | NOT STARTED |
| Password | argon2id + per-user salt | NOT STARTED |
| TLS | TLS 1.2+ (cpp-httplib SSLServer) | NOT STARTED |
| Input Validation | Max length, type check | PARTIAL |
| SQL Injection | Prepared statements ALL queries | NOT STARTED |
| Rate Limiting | std::atomic, per-IP | PARTIAL |
| CORS | Whitelist origins | NOT STARTED |
| Audit Log | Log ALL mutations | PARTIAL |
| Token Revocation | SQLite persistent | NOT STARTED |
| TURN Creds | HMAC time-limited (1h TTL) | NOT STARTED |
| coturn Security | denied-peer-ip, no-tcp-relay, TLS | NOT STARTED |
| Agent Auth | Per-machine JWT token | NOT STARTED |

# 11. DEPLOYMENT

## 11.1. Docker Compose

services:

hub32api: build: . | ports: 11081 | volumes: ./data:/app/data

coturn: image: coturn/coturn | network_mode: host

nginx: image: nginx:alpine | ports: 443, 80

prometheus: (optional) | grafana: (optional)

## 11.2. Firewall

| Port | Proto | Service | Mô tả |
| --- | --- | --- | --- |
| 443 | TCP | nginx + coturn TLS | HTTPS + TURN TLS |
| 3478 | UDP | coturn STUN | STUN binding |
| 40000-49999 | UDP | coturn relay | WebRTC media |
| 80 | TCP | certbot | Let’s Encrypt |

## 11.3. Agent Installer

- Silent: msiexec /i hub32-agent.msi /qn SERVER_URL=https://hub32.example.com

- Auto-start Windows Service, auto-update via heartbeat

- Group Policy deployment cho toàn trường

# 12. PHỤ LỤC

## 12.1. Glossary

| Thuật ngữ | Định nghĩa |
| --- | --- |
| SFU | Selective Forwarding Unit – forward media, không transcode |
| TURN | Traversal Using Relays around NAT |
| STUN | Session Traversal Utilities for NAT |
| ICE | Interactive Connectivity Establishment |
| DTLS | Datagram TLS – mã hóa WebRTC |
| SRTP | Secure RTP – mã hóa media |
| DXGI | DirectX Graphics Infrastructure – capture màn hình |
| NVENC | NVIDIA Video Encoder – hardware H.264 |
| QSV | Quick Sync Video – Intel iGPU encode |
| WAL | Write-Ahead Logging – SQLite concurrent access |
| Simulcast | Gửi nhiều quality layers, SFU chọn phù hợp |

## 12.2. Timeline

| Phase | Tuần | Người-ngày | Output |
| --- | --- | --- | --- |
| Phase 0: Security | 1 | 5 | JWT RS256, TLS, argon2id |
| Phase 1: Database | 2 | 5 | Schema, repos, CRUD API |
| Phase 2: Agent Comm | 3 | 5 | Registration, heartbeat, commands |
| Phase 3: mediasoup | 4-5 | 10 | SFU, signaling API, coturn |
| Phase 4: Agent WebRTC | 5-6 | 10 | H.264 encode, WebRTC producer |
| Phase 5: Dashboard | 6-7 | 10 | Web UI, grid, controls |
| Phase 6: Demo | 7-8 | 5 | Teacher broadcast |
| Phase 7: Testing | 8-9 | 10 | Load test, security audit |
| Phase 8: Deploy | 9-10 | 5 | Docker, TLS, installer |
| Tổng | 10 tuần | 65 |  |